## Sheet1 (hidden)
Item Description | QTY | Unit | Unit Rate | Total amount | Total amount with VAT | Month
1.Surveyor with total station | 250 | Hr | 34.62 | 8655 | 9953.25 | December
2.Surveyor with total station | 1 | Month | 9000 | 9000 | 10350 | January
3.Surveyor with total station | 1 | Month | 9000 | 9000 | 10350 | November
4.Man power (Carpenter) ismail | 624 | Hr | 18 | 11232 | 12916.8 | December
5.Man power (Steel Fixer) ismail | 229 | Hr | 18 | 4122 | 4740.3 | December
6.Man power (Helper) ismail | 1065 | Hr | 15 | 15975 | 18371.25 | December
7.Man power (Carpenter) ismail | 363 | Hr | 18 | 6534 | 7514.1 | November
8.Man power (Steel Fixer) ismail | 123 | Hr | 18 | 2214 | 2546.1 | November
9.Man power (Tea boy) ismail | 48 | Hr | 15 | 720 | 828 | November
10.Man power (Helper) ismail | 580 | Hr | 15 | 8700 | 10005 | November
man power (eng abdelrhman) |  |  |  |  | 4000 | December
man power (eng abdelrhman) |  |  |  | 29319 | 29319 | January
man power (eng abdelrhman) |  |  |  | 69000 | 69000 | February
Stuff modern team |  |  |  | 45123 | 45123 | january
Stuff modern team |  |  |  | 52500 | 52500 | February
15. Equipment (10 Ton Fork Lift with operator) MAGED | 300 | Hr | 67.3076 | 20192.28 | 23221.122 | December
16. Equipment (backhoe loader with operator) MAGED | 250 | Hr | 63.4615 | 15865.375 | 18245.1812 | December
17. Equipment (backhoe loader with operator) MAGED | 260 | Hr | 63.4615 | 16499.99 | 18974.9885 | November
18. Equipment (backhoe loader with operator) MAGED | 260 | Hr | 67.3076 | 17499.976 | 20124.9724 | November
19. Equipment (backhoe loader with operator) MAGED |  |  |  | 18000 | 18000 | January
|  |  |  | 18000 | 18000 | February
Exacavator (Eng abdelerhman) |  |  |  | 24150 | 24150 | February
Personal Remittances (Eng ahmed el berry) |  |  |  | _ | 200 | _
Personal Remittances (Eng ahmed el berry) |  |  |  | _ | 500 | _
Personal Remittances (Eng ahmed el berry) |  |  |  | _ | 40 | _
Personal Remittances (Eng ahmed el berry) |  |  |  | _ | 30 | _
Personal Remittances (Eng ahmed el berry) |  |  |  | _ | 500 | _
Fire extingushers (Eng ahmed el berry) |  |  |  | _ | 414 | _
Safety jackets (Eng ahmed el berry) |  |  |  | _ | 150 | _
NITOPROOF 10 & RENDEROC FC (20 KG) |  |  |  | _ | 3852 | _
Site procurment (Disel,Building material,water,material transportation...etc (Eng abdelrhman) |  |  |  | _ | 5500 | _
Site procurment (Disel,Building material,water,material transportation...etc (Eng ahmed elberry) |  |  |  | _ | 3177.45 | _
Site procurment (Disel,Building material,water,material transportation...etc (Eng ahmed elberry) |  |  |  | _ | 2052 | _
Site procurment (Disel,Building material,water,material transportation...etc (Eng ahmed elberry) |  |  |  | _ | 11414 | _
Site procurment (Disel,Building material,water,material transportation...etc (Eng ahmed elberry) |  |  |  | _ | 1946 | _
Site procurment (Disel,Building material,water,material transportation...etc (Eng ahmed elberry) |  |  |  | _ | 1918 | _
Site procurment (Disel,Building material,water,material transportation...etc (Eng ahmed elberry) |  |  |  | _ | 8615 | _
Total concerte to finalize |  |  |  | _ | 401000 | _ | 87000
third party inspection |  |  |  |  | 15000
Site procurment (Disel,Building material,water,material transportation...etc (Eng abdelrhman) |  |  |  | _ | 9000 | _
Site procurment (Disel,Building material,water,material transportation...etc (Hany) |  |  |  | _ | 5000 | _
subcontractor (Abo moaz) |  |  |  |  | 100000 | UP TO DATE | 10000
Bus rent |  |  |  |  | 48300 | UP TO DATE | 13800
Site procurment (Disel,Building material,water,material transportation...etc (Eng abdelrhman) |  |  |  | _ | 22000 | _
1068841.5141
cash in | cash out | pending to be paid

## Sheet2
|  | Cost sheet for RAK project included | Labour& stuff Cost | Materials Cost | Equipment Cost | Accomodation | Transportation | others
|  | Item Description | Month | Cash out | paid | pending to be paid
|  | Surveyor with total station | November | 9953.25 | 0
cash in | SAR | Surveyor with total station | December | 10350
5% DOWN PAYMENT | 482052.5 | Surveyor with total station | January | 10350
IPA01 | 159031 | (all labours included (ismail) | January | 32593.75
| 641083.5 | (all labours included (ismail) | February | 48802.75
|  | (all labours included (ismail) | March | 71225
|  | Stuff modern team | January | 71220
|  | Stuff modern team | February | 87220
|  | Stuff modern team | March | 58220
|  | Equipment (10 Ton Fork Lift with operator) MAGED | December | 18576.8976
|  | Equipment (backhoe loader with operator) MAGED | December | 19704.7957
|  | Equipment (backhoe loader with operator) MAGED | November | 11610.561
|  | Equipment (10 Ton Fork Lift with operator) MAGED | November | 11610.561
|  | Equipment (10 Ton Fork Lift with operator) MAGED | January | 3096.15
|  | Equipment (backhoe loader with operator) MAGED | January | 18974.99
|  | Equipment (backhoe loader with operator) MAGED | February | 12698.65
|  | Equipment (backhoe loader with operator) MAGED | March | 1459.61
|  | Site procurment (Plastic rolls, PVC green mesh,Transportation)(Eng ahmed el berry) | Up to date | 30000 | 30000
|  | Site procurment (Disel,Building material,Food, transportation...etc (Eng ahmed aboud) | Up to date | 14000 | 14000
|  | Site procurment (Disel,Building material,Food, transportation...etc (Abdelrehiem) | Up to date | 27000 | 27000
|  | Bus rent | January | 2300 | 0
|  | Bus rent | February | 11500
|  | Bus rent | March | 11500
|  | accent car | November | 2530 | 2530
|  | accent car | December | 2600 | 2600
|  | accent car | January | 2530 | 2530
|  | accent car | February | 2600 | 2600
|  | accent car | March | 2600 | 2600
|  | car ( wanyet) | January | 6325 | 6325
|  | Car (wanyet) | February | 6325 | 6325
|  | Car (wanyet) | March | 6325 | 6325
|  | third party inspection | Up to date | 5000
|  | concerete | Up to date | 17500 | 17500
|  | BRC materials | Up to date | 12117 | 12117
|  | Accomodation (Labours) | Up to date | 12600 | 12600
|  | Accomodation (junior stuff) | Up to date | 35600 | 23000
|  | Accomodation (senior stuff) | Up to date
|  | Accomodation (Eng.A.elberry) (Hotel) | Up to date | 3000 | 3000
|  | Total amount |  | 708618.9653 | 168052 | 540566.9653